## Sheet1
No | Package | Type | Project | ComponentName | TaskID | MT_Number | ItemName | MT_Needed | Type of Comment | BB | Baseline | Database | ItemRevision | Owner Contact | Task Jira | TaskGroup | Tester | PeerReviewer | Status Review | ELOC Assigned | ELOC Recheck With Tool | LOC Complete | Estimation base TOOL | Actual hour | Status | Release Date | Planned Start | Planned End | Start | End | Status Result | C0 | C1 | MCDC | OPL/Defect | Reason For code coverage | Reason for Fail Testcase | Remark
37 | 20200414 | PSW | HHT_VX1_IBooster_Gen2_BL2 | iBoosterGen2\rb\as\hht\vx1\netpr\src | 1417373 | - | ComScl_UserDefinedProcessing.c | - | Auto | 80428 | BL2 | HHT_VX1_IB2_Carbon_Int | - | YUAN Jessica(BEG/ESW-CN) |  | - | bang.nguyen-duy |  |  | 322 | 322 | 322 | 5.72 | 2 | Complete & Closed | 2020-04-17 | 2020-04-14 | 2020-04-17 | 2020-04-14 | 2020-04-14 | OK | 100% | 100% | 100% | None
38 | 20200414 | PSW | HHT_VX1_IBooster_Gen2_BL2 | iBoosterGen2\rb\as\hht\vx1\netpr\gen\Cubas\CAN_OBD_Off | 1417373 | - | ComScl_Scl_ADCM_BU_2_Rx.c | - | Auto | 80428 | BL2 | HHT_VX1_IB2_Carbon_Int | - | YUAN Jessica(BEG/ESW-CN) |  | - | bang.nguyen-duy |  |  | 268 | 268 | 268 | 4.76 | 2 | Complete & Closed | 2020-04-17 | 2020-04-14 | 2020-04-17 | 2020-04-15 | 2020-04-15 | OK | 100% | 100% | 100% | None
39 | 20200414 | PSW | HHT_VX1_IBooster_Gen2_BL2 | iBoosterGen2\rb\as\hht\vx1\netpr\gen\Cubas\CAN_OBD_Off | 1417373 | - | ComScl_Scl_ADCM_FD_1_Rx.c | - | Auto | 80428 | BL2 | HHT_VX1_IB2_Carbon_Int | - | YUAN Jessica(BEG/ESW-CN) |  | - | bang.nguyen-duy |  |  | 275 | 275 | 275 | 4.88 | 2 | Complete & Closed | 2020-04-17 | 2020-04-14 | 2020-04-17 | 2020-04-15 | 2020-04-15 | OK | 100% | 100% | 100% | None
40 | 20200414 | PSW | HHT_VX1_IBooster_Gen2_BL2 | iBoosterGen2\rb\as\hht\vx1\netpr\gen\Cubas\CAN_OBD_Off | 1417373 | - | ComScl_Scl_IFV300_1_Rx.c | - | Auto | 80428 | BL2 | HHT_VX1_IB2_Carbon_Int | - | YUAN Jessica(BEG/ESW-CN) |  | - | bang.nguyen-duy |  |  | 267 | 267 | 267 | 4.74 | 2.5 | Complete & Closed | 2020-04-17 | 2020-04-14 | 2020-04-17 | 2020-04-15 | 2020-04-15 | OK | 100% | 100% | 100% | None
46 | 20200414 | PSW | EC_245950_NIO_ESX_ESPHevX_DTC_BSS01_SP01 | rba\BldrCmp\src | 1417493 | - | rba_BldrCmp_31RoutineControl_Chkpd.c | - | Auto | None | BSS01_SP01 | NextEV_IB2_Int | - | Nguyen Van Tam (RBVH/EJV42) |  | - | bang.nguyen-duy |  |  | 194 | 194 | 194 | 3.44 | 3 | Complete & Closed | 2020-04-17 | 2020-04-14 | 2020-04-17 | 2020-04-15 | 2020-04-15 | OK | 100% | 100% | 100% | None
47 | 20200414 | PSW | EC_245950_NIO_ESX_ESPHevX_DTC_BSS01_SP01 | rba\BldrCmp\src | 1417493 | - | rba_BldrCmp_31RoutineControl_Er.c | - | Auto | None | BSS01_SP01 | NextEV_IB2_Int | - | Nguyen Van Tam (RBVH/EJV42) |  | - | bang.nguyen-duy |  |  | 321 | 321 | 321 | 5.7 | 6 | Complete & Closed | 2020-04-17 | 2020-04-14 | 2020-04-17 | 2020-04-16 | 2020-04-16 | OK | 100% | 100% | 100% | None
48 | 20200414 | PSW | EC_245950_NIO_ESX_ESPHevX_DTC_BSS01_SP01 | rba\BldrCmp\src | 1417493 | - | rba_BldrCmp_31RoutineControl.c | - | Auto | None | BSS01_SP01 | NextEV_IB2_Int | - | Nguyen Van Tam (RBVH/EJV42) |  | - | bang.nguyen-duy |  |  | 52 | 52 | 52 | 0.92 | 1 | Complete & Closed | 2020-04-17 | 2020-04-14 | 2020-04-17 | 2020-04-17 | 2020-04-17 | OK | 100% | 100% | 100% | None
49 | 20200414 | PSW | EC_245950_NIO_ESX_ESPHevX_DTC_BSS01_SP01 | rba\BldrCmp\src | 1417493 | - | rba_BldrCmp_34RequestDownload.c | - | Auto | None | BSS01_SP01 | NextEV_IB2_Int | - | Nguyen Van Tam (RBVH/EJV42) |  | - | bang.nguyen-duy |  |  | 209 | 209 | 209 | 3.71 | 3 | Complete & Closed | 2020-04-17 | 2020-04-14 | 2020-04-17 | 2020-04-17 | 2020-04-17 | NG | 100% | 100% | 75% | OPL
50 | 20200414 | PSW | EC_245950_NIO_ESX_ESPHevX_DTC_BSS01_SP01 | rba\BldrCmp\src | 1417493 | - | rba_BldrCmp_37RequestTransferExit.c | - | Auto | None | BSS01_SP01 | NextEV_IB2_Int | - | Nguyen Van Tam (RBVH/EJV42) |  | - | bang.nguyen-duy |  |  | 67 | 67 | 67 | 1.19 | 2 | Complete & Closed | 2020-04-17 | 2020-04-14 | 2020-04-17 | 2020-04-17 | 2020-04-17 | OK | 100% | 100% | 100% | None
51 | 20200414 | PSW | EC_245950_NIO_ESX_ESPHevX_DTC_BSS01_SP01 | rba\BldrCmp\src | 1417493 | - | rba_BldrCmp_DataHdl.c | - | Auto | None | BSS01_SP01 | NextEV_IB2_Int | - | Nguyen Van Tam (RBVH/EJV42) |  | - | bang.nguyen-duy |  |  | 202 | 202 | 202 | 3.59 | 3 | Complete & Closed | 2020-04-17 | 2020-04-14 | 2020-04-17 | 2020-04-17 | 2020-04-17 | OK | 100% | 100% | 100% | None
111 | 20200416_1 | PSW | Adapt_236246_SMART_BBM_Ibooster_E2_SP3 | GEEA2_0_IB2_SMART_Deuterium_Int\iBoosterGen2\rb\as\ms\core\app\dcom\RBAPLCust\src\DcmAppl_22_rdbi.c | 1411690 | - | DcmAppl_22_rdbi.c | - | Auto | 81519 | - | GEEA2_0_IB2_SMART_Deuterium_Int | - | LIANG Xin (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 1434 | 1434 | 1434 | 25.49 | 6 | Ready for review |  |  | 2020-04-24 | 2020-04-22 | 2020-04-22 | OK | 100% | 100% | 100% | OPL |  |  | Count for 21 Apr
134 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\Cubas\src\Dcm_CNMS\DcmAppl_DcmSwitchCommunicationControl.c | 1416606 | - | DcmAppl_DcmSwitchCommunicationControl.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 84 | 84 |  | 1.49 |  |  |  |  | 2020-04-30
135 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLCust\src\common\DCOMIF.c | 1416606 | - | DCOMIF.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 7 | 7 |  | 0.12 |  |  |  |  | 2020-04-30
136 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLCust\src\common\RBAPLCUST_DiagnosticSessionControl.c | 1416606 | - | RBAPLCUST_DiagnosticSessionControl.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 259 | 259 |  | 4.6 |  |  |  |  | 2020-04-30
137 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLCust\src\common\RBAPLCUST_RBDI_NVMData_Prj.c | 1416606 | - | RBAPLCUST_RBDI_NVMData_Prj.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 140 | 140 |  | 2.48 |  |  |  |  | 2020-04-30
138 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLCust\src\iBooster\RBAPLCUST_RDBI_AnalogData.c | 1416606 | - | RBAPLCUST_RDBI_AnalogData.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 313 | 313 |  | 5.56 |  |  |  |  | 2020-04-30
139 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLCust\src\ESP\RBAPLCUST_RDBI_IOCtrlState.c | 1416606 | - | RBAPLCUST_RDBI_IOCtrlState.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 144 | 144 |  | 2.56 |  |  |  |  | 2020-04-30
140 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLCust\src\common\RBAPLCUST_ReadDTCInformation.c | 1416606 | - | RBAPLCUST_ReadDTCInformation.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 59 | 59 |  | 1.04 |  |  |  |  | 2020-04-30
141 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLCust\src\ESP\RBAPLCUST_RoutineControl_APBMi.c | 1416606 | - | RBAPLCUST_RoutineControl_APBMi.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 354 | 354 |  | 6.29 |  |  |  |  | 2020-04-30
142 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLCust\src\iBooster\RBAPLCUST_RoutineControl_iBoosterActuatorTest.c | 1416606 | - | RBAPLCUST_RoutineControl_iBoosterActuatorTest.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 186 | 186 |  | 3.3 |  |  |  |  | 2020-04-30
143 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLCust\src\common\RBAPLCUST_VariandCode.c | 1416606 | - | RBAPLCUST_VariandCode.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 159 | 159 |  | 2.82 |  |  |  |  | 2020-04-30
144 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLOBD\src\RBAPLOBD_Data.c | 1416606 | - | RBAPLOBD_Data.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 199 | 199 |  | 3.53 |  |  |  |  | 2020-04-30
145 | 20200416_1 | PSW | GWM_B30_HP | GWM_B30_HP_Int\CNMSESPHevX\rb\as\gwm\core\app\dcom\RBAPLOBD\src\RBAPLOBD_Global.c | 1416606 | - | RBAPLOBD_Global.c | - | Auto | B30_8DCT_HP: 80432; A30_DHT_HP: 81558 | BSS07 | GWM_B30_HP_Int | - | XU Zhuofan (CC-AS/EVA-SW33-CN) |  | - | bang.nguyen-duy |  |  | 6 | 6 |  | 0.1 |  |  |  |  | 2020-04-30
165 | 20200416_1 | PSW | BYD_IPB_SW_Mainstream_BL05_Defect |  | 1405296 | - | RBA_NDS_Complex_Callout.c | - | Auto | None | BL05 | BYD_IPB_BL05_Int | - | GUO Sasa (CC-AS/EVA-SW3-CN) |  | - | bang.nguyen-duy |  |  | 803 | 803 | 803 | 14.27 | 14 | Ready for review | 2020-04-21 | 2020-04-20 | 2020-04-21 | 2020-04-20 | 2020-04-21 | NG | 100% | 100% | 90% | OPL | At line #508 & line #512 cannot cover MCDC because variable l_DriverPresent_B. At line 479 BOOL l_DriverPresent_B = true;
184 | 20200417 | PSW | 231839_DearCC_IC321_ESP9.3_BSS02_CAN_MATRIX_VARTABLE | DearCC_RBEI_ESP93CP_Carbon_Int\MainstreamF30\rb\as\cnms_core\app\dsm\RBVAR\src\RBVAR_SystemStateManagement_COMMON.c | 1417738 | - | RBVAR_SystemStateManagement_COMMON.c | - | Auto | None | BSS02 | DearCC_RBEI_ESP93CP_Carbon_Int | - | Resmi George (RBEI/ESC1) |  |  | bang.nguyen-duy |  |  | 180 | 180 | 180 | 3.2 | 2 |  |  |  | 2020-04-24 | 2020-04-22 | 2020-04-22 | OK | 100% | 100% | 90% | None
[9 empty] | Database | ComponentName | ItemName
[9 empty] | GEEA2_0_IB2_SMART_Deuterium_Int | \iBoosterGen2\rb\as\ms\core\app\dcom\RBAPLCust\src\ | DcmAppl_22_rdbi.c
[9 empty] | BYD_IPB_BL05_Int |  | RBA_NDS_Complex_Callout.c
[9 empty] | DearCC_RBEI_ESP93CP_Carbon_Int | \MainstreamF30\rb\as\cnms_core\app\dsm\RBVAR\src\RBVAR_SystemStateManagement_COMMON.c | RBVAR_SystemStateManagement_COMMON.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src\rba_BldrCmp_Cfg_CheckMem.c | rba_BldrCmp_Cfg_CheckMem.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src\rba_BldrCmp_Cfg_Com.c | rba_BldrCmp_Cfg_Com.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src\rba_BldrCMP_Cfg_CRC.c | rba_BldrCMP_Cfg_CRC.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\Infrastruct\TestEnv\src\rba_BldrCmp_Cfg_DebugSupport.c | rba_BldrCmp_Cfg_DebugSupport.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src\rba_BldrCmp_Cfg_FlashIf.c | rba_BldrCmp_Cfg_FlashIf.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src\rba_BldrCmp_Cfg_Functions.c | rba_BldrCmp_Cfg_Functions.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src\rba_BldrCmp_Cfg_NvmIf.c | rba_BldrCmp_Cfg_NvmIf.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src\rba_BldrCmp_Cfg_PrjFunctions.c | rba_BldrCmp_Cfg_PrjFunctions.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\ApplicationLayer\rba_BldrCmp\src\rba_BldrCmp_Cfg_SecA.c | rba_BldrCmp_Cfg_SecA.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\Infrastruct\TestEnv\src\rba_BldrCmp_Cfg_TestServices.c | rba_BldrCmp_Cfg_TestServices.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\Infrastruct\TestEnv\src\rba_BldrCmp_Cfg_TestServices_TaskMon.c | rba_BldrCmp_Cfg_TestServices_TaskMon.c
[9 empty] | JAC_ESP93_Carbon_Int | rba\Bldr\config\Infrastruct\TestEnv\src\rba_BldrCmp_Cfg_TestStackEval.c | rba_BldrCmp_Cfg_TestStackEval.c
Note on E17: EXTERNAL Nguyen Trung Hieu (Ban Vien, RBVH/EPS45): Count for 21Apr
Note on I17: EXTERNAL Nguyen Trung Hieu (Ban Vien, RBVH/EPS45): \\10.184.143.103\d\vivi\BV\DB\16Apr
Note on E31: EXTERNAL Nguyen Trung Hieu (Ban Vien, RBVH/EPS45): \\10.184.143.103\d\vivi\BV\DB\18Apr EXTERNAL Nguyen Trung Hieu (Ban Vien, RBVH/EPS45): Wrong name: Int is correct Geely_Beryllium2_In Geely_Beryllium2_OBD_China6_In